## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP
0 | 9/5 - 9/12 | 0. Completed iteriation 0 SPPP 1. Completed iteration 0 Risk management 2. Completed Git/GitHub pull, push, merge, and commit operations 3. Completed GitHub doc. folder, Readme.md, and Team3.md | 0. Learn/review git/GitHub, SpringBoot, mySQL 6. Set up git, java, maven, and mySql environment | 1. Watch team discussion and meeting records 2. Work on various SPPP components 5. Coordinate meeting plans 7. Research similar application, prepare presentatio | 1. SPPP and risk management 2. Discuss the requirements and other agenda for the project |  |  | 6 | 6 | 0 | 55.5 | 44.5 | 11 | 15 | 10 | 1 | 0 | 0 | 8 | 8 | 2.5
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Abigya Devkota | 1. Proposed high level requirements 2. Timeline 3. Code commit guideline and git branching strategy | [7 empty] | 1. actively communicated with team members through discord
Jianle Xie | 1. Project Overview 2. Risk Management |  |  |  | Iteration 0 presentation | Team3.md |  |  | 1. actively communicated with team members through discord
Yuxuan Wang
Jingjing Tang
weihao Mai

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Jianle Xie
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/05 - 9/12 | 11 | 9 | 2 | 0 - learn git, springboot, watch several tutorials 2 - wrote Overview (SPPP) 5 - coordinate meeting plans, send reminders to team members 6 - set up git, gitHub 7 - research similar products, prepare presentation | 4 |  | 1 |  |  | 1 | 1 | 2 | 1. worked on Overview, Risk Management, and Related Work of SPPP 2. Set up git/GitHub, create Lab_1 branch, create Team3.md file, upload bio onto Team3.md file 3. Participate in Iteration 0 presentation | 1. Not familiar with git/github, unware of it's functionalities 2. Not proficient with Springboot, unable to take full advantage of it's capabilities 3. Communication is not clear. Task assignments / project direction is not clear. Followup with all team member to ensure all individual tasks are handed in (Lab1 and Progressive report) | 1. Finished with git/github tutorials, able to create branch, add changes, commit changes, and push to github via terminal. Understand various branching strategies. 2. Finished multiple SpringBoot tutorials, able to run demo application on local host with Get/Post/Update/Delete mapping functionality with testing from Postman 3. Successful iteration 0 meeting, project plan hashed out, roles assigned, SPPP finished for iteration 0 | 0. continue to learn SpringBoot, explore intergration of database with Springboot, learn Junit testing 1. continue to define requirements 5. coordinate with all team member for next meeting schedule. Finalize security leader role, | 6

## Jingjing Tang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 10 | 8 | 2 | 0 - learn Git and Spring Boot 1 - watch team discussion and meeting record 5 - make project plan 6 - set up git and working environment | 3 | 2 |  |  |  | 2 | 1 |  | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Weihao Mai
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 10 | 9 | 1 | 0 - learn Git, Spring Boot and Mysql 1 - watch team discussion and meeting record 5 - make project plan 6 - set up git, java and Mysql environment | 4 | 2 |  |  |  | 1 | 2 |  | 1.Modified the team.md document and added a self introduction | 1. not familar with git and github 2.not know how to push code to github 3. not familar with Mysql 4. not familar with Spring boot | 1. finish Springboot tutorial in 2 weeks, be able to create simple Springboot hello world project next week 2. learn how to build databasr using Mysql | 0 - continue to learnSpringboot and Mysql 1 - continue to define requirements 3 - implement database using Mysql | 9

## Abigya Devkota
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05/23-09/12/23 | 14.5 | 11.5 | 3 | 0 - learn git and spring boot 1 - discuss project with team 5 - make project plan 6 - set up git/springboot/maven 7 - presentation | 3 | 3 |  |  |  | 2 | 3 | 0.5 | 1. Contribute to high level requirements, project time and git guidelines 2. Begin project design for review 3. Participate in Iteration 0 presentation | 1. Deciding on project complexity per team member's familiarity with chosen tech stack 2. Deciding on database that's easy enough to implement with spring boot | 1. Create data model and practice with shell project 2. Research H2 database | 0- continue learning about using db with springboot 2 - build app with team | 10

## Yuxuan Wang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05/23-09/12/23 | 10 | 7 | 3 | 0 - learn Git and Spring Boot 1 - team discussion and meeting 5 - make project plan 6 - set up git and working environment | 1 | 3 |  |  |  | 2 | 1 |  | 1. Contribute to SPPP_RiskManagement and SPPP file 2. Set up git, commit a intro paragraph on git | 1. Not familar with Git desktop 2. Not familiar with automated testing tools that can be embedded with Github 3. Not familiar with front-end or db implement with Spring boot | 1.Research Git Desktop tutorial on Youtube 2. Research 3. Research on thymeleaf package in Spring boot for processing and creating CSS file. Check on integrate database with MySql.(could switch to H2 for its easier and in-memory usage) | 0 - continue learning db and front-end in Spring boot 1 - start build app with team | 10