## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP
0 | 9/5 - 9/12 | 0. Completed iteriation 0 SPPP 1. Completed iteration 0 Risk management 2. Completed Git/GitHub pull, push, merge, and commit operations 3. Completed GitHub doc. folder, Readme.md, and Team3.md | 0. Learn/review git/GitHub, SpringBoot, mySQL 6. Set up git, java, maven, and mySql environment | 1. Watch team discussion and meeting records 2. Work on various SPPP components 5. Coordinate meeting plans 7. Research similar application, prepare presentatio | 1. SPPP and risk management 2. Discuss the requirements and other agenda for the project |  |  | 6 | 6 | 0 | 55.5 | 44.5 | 11 | 15 | 10 | 1 | 0 | 0 | 8 | 8 | 2.5
1 | 9/13 - 9/25 | 1. Project requirements and scope are further clarified 2. Deliver mock EMS_V1 with H2 database to GitHub 3. SDD completed 4. Update Risk Management and identify new risk towards the project 5. Completed tasks on PrivtalTracker (Create/Update/View/Delete functionalities) 6. Coded backend classes for employee and Credentials with all unit tests 7. Created three database tables using H2 database structure 8. Finish Spring Security part 9. Integreated frontend, backend, and database layers 10. Deliver successful built EMS_V1 with backend and frontend integration | 0. Learning Gi, Spring boot with database implemenation, UI designs, React, VSCode, JWT authentication, Spring Security and database. 3. Make changes to backend algorithm and add new structures for Junit Tests. Intergrate mock EMS_V1 with Mock PostGres db and/or H2 db. Create 5 databse table by using MYSQL for security testing. Implement DAO test. 4. Create Junit Tests for backend classes including Model, Controller and Repository for Employee and Credential Parts. Test mock EMS_V1 with Mock PostGres db/H2. Test UI functions on static UI page (buttons, etc). Test after add Spring Security mock security codes. Test backend , frontend and database to ensure code was runnable and performed minimal functionality. 6. Set up Junit and Maven environment. Set up git and environment in intellij. Configure new branch for my own updates and public branch for whole backend & database design. Set up an environment on my computer to try to complete the User's CRUD first for Spring Security testing. Set up an environment for User and Role's CRUD, DAO and entity testing, add the methods of assigning roles, search the role of the current user, and return the common result, add swagger2 for testing. add springsecurity part. Combine spring boot project with front end code, created PR for merging | 1. Clarified requirment for project. Communicated with team through zoom. Watch team discussion and meeting record. Understand database and backend design requirement for iteration1. 2. Work on various part of SDD 5. Meet up with group members to assign modules and tasks. Coordinate meeting/go over Mock EMS_V1. Split project into 3 component (backend, frontend, security), assigned sub_teams to each component. Go over Iteration0 feedback and areas to improve. Configure Git, SpringBoot Maven, H2 dependencies and related work regarding backend. Design class diagram. Intergrate all components and debug issues. 7. Wrote out the design document for backend and database algorithms. Primary intergration of backend with frontend | 1. SDD and updated Risk Management 2. Subdivide the group into Frontend, Backend, and Security | 4 | 6 | 7 | 7 | 0 | 172 | 143.5 | 28.5 | 36 | 9 | 14 | 23 | 19 | 20.5 | 18 | 4
2 | 9/26 - 10/9 | 0 - learn/understand spring security, JWT authentication, React integration, Unit Testing 1 - implement request vacation funcationality via TDD method, make login and registration page 4 - front/back/security integration testing, request vacation testing, Unit Testing 5 - communicate security team for integration | 0 - learn/understand spring security, JWT authentication, React integration, Unit Testing 4 - front/back/security integration testing, request vacation testing, Unit Testing | 1 - implement request vacation funcationality via TDD method, make login and registration page 5 - communicate security team for integration | 1. Security Design in SDD and update Risk Management | 1 | 2 | 1 | 0 | 1 | 111 | 100 | 11 | 42 | 4 | 8 | 0 | 38 | 4 | 4 | 0
3 | 10/10 - 10/17 | 0 - learn role base authorization, docker, docker setup for postgres 1 - check up vacation functionality for backend 2 - update SDD UI 3 - make separate homepage based on role, debug registration page 5 - schedule final presetation 6- add docker setup for postres 7 - make final application demo, update privotalTracker | 0 - learn role base authorization, docker, docker setup for postgres 3 - make separate homepage based on role, debug registration page 6- add docker setup for postres | 1 - check up vacation functionality for backend 2 - update SDD UI 5 - schedule final presetation 7 - make final application demo, update privotalTracker | 1. Update Risk Management/Close out Risks 2. Update SPPP personal hours | 0 | 2 | 2 | 0 | 2 | 43 | 29 | 14 | 15 | 4 | 0.5 | 0 | 4 | 0.5 | 4 | 1

## studentName_template
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Abigya Devkota | 1. Proposed high level requirements 2. Timeline 3. Code commit guideline and git branching strategy | UI unit tests for create, update, home page , and view pages | 1. Software architecture diagrams | Added testing documentation for react tests | Iteraion 0 presentation | 1- integration of project components 2- docker setup and debugging issues | used postman to test api calls ui uni tests | Docker setup, branching setup, r esolving merge conflicts, project pom setup | 1. actively communicated with team members through discord 2. participated in iteration demos 3. troubleshoot problems with team members
Jianle Xie | 1. Project Overview 2. Related Work 3. Risk Management | 1. Create new Staff 2. Update staff info 3. View staff info 4. Delete staff | 1. Introduction 2. User Interface | Manual Testing Acceptance Testing | Iteration 0 presentation UI demo presentation Final demo presentation | 1. Team3.md 2. Frontend branch 3. docker_setup_v3 | Manual testing spreadsheet |  | 1. actively communicated with team members through discord
Yuxuan Wang | 1. Quality Metric Assurance |  | Design Pattern |  | Iteration 1 presentation
Jingjing Tang |  |  | Class diagram |  | Iteration 1 presentation
weihao Mai |  |  | Security design | secruity test |  | modify Team3.md |  |  | 1. communicated with team members through discord
Zhiwei Lin |  |  | Business Logic | spring-scurity | iteration 2 | 1.add hr-masery demo 2. add spring-security part | using swagger to test methods | my branch, under demo and code | 1. usually communicated with leader
HaoLun Li |  |  | Database design

## Jianle Xie
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/05 - 9/12 | 11 | 9 | 2 | 0 - learn git, springboot, watch several tutorials 2 - wrote Overview (SPPP) 5 - coordinate meeting plans, send reminders to team members 6 - set up git, gitHub 7 - research similar products, prepare presentation | 4 |  | 1 |  |  | 1 | 1 | 2 | 1. worked on Overview, Risk Management, and Related Work of SPPP 2. Set up git/GitHub, create Lab_1 branch, create Team3.md file, upload bio onto Team3.md file 3. Participate in Iteration 0 presentation | 1. Not familiar with git/github, unware of it's functionalities 2. Not proficient with Springboot, unable to take full advantage of it's capabilities 3. Communication is not clear. Task assignments / project direction is not clear. Followup with all team member to ensure all individual tasks are handed in (Lab1 and Progressive report) | 1. Finished with git/github tutorials, able to create branch, add changes, commit changes, and push to github via terminal. Understand various branching strategies. 2. Finished multiple SpringBoot tutorials, able to run demo application on local host with Get/Post/Update/Delete mapping functionality with testing from Postman 3. Successful iteration 0 meeting, project plan hashed out, roles assigned, SPPP finished for iteration 0 | 0. continue to learn SpringBoot, explore intergration of database with Springboot, learn Junit testing 1. continue to define requirements 5. coordinate with all team member for next meeting schedule. Finalize security leader role, | 6
2 | 09/13-9/19 | 12.5 | 11 | 1.5 | 0 - contine learn springBoot with database implemenation, learn UI designs 2 - work on UI design via figmo 3 - intergrate mock EMS_V1 with Mock PostGres db and/or H2 db 4 - test mock EMS_V1 with Mock PostGres db/H2 5 - coordinate meeting/go over Mock EMS_V1 | 6 |  | 2 | 1 | 1 | 1 |  |  | 1. worked on SDD UI components 2. deliver mock EMS_V1 with H2 database to GitHub | 1. Not familiy with UI/React 2. Unsure if mock MCV with H2 database will work | 1. Continue React tutorial 2. Successful mock EMS_V1 (MCV model) with H2 database with dummy entries upload to gitHub | 0. Learn React 1. continue to define requirements and enbolden the system structure 2. make static React pages | 10
3 | 9/20-9/27 | 21 | 20.5 | 0.5 | 0 - learn React, VSCode, understand JWT authentication 2 - review/update SDD plans, make static UI pages 4. test UI functions on static UI page (buttons, etc) 5 - split project into 3 component (backend, frontend, security), assigned sub_teams to each component. Go over Iteration0 feedback and areas to improve. Update risk management 7 - primary intergration of backend with frontend | 10 |  | 2 |  | 6 | 0.5 |  | 2 | 1. Deliver successful built EMS_V1 with backend and frontend integration 2. Complete first review of SDD plans 3. Completed tasks on PrivtalTracker (Create/Update/View/Delete functionalities) 4. Update Risk Management and identify new risk towards the project | 1. Intergation with security is still a current concern 2. Additional functionalities needs to implemented i.e. Request Vacation 3. Additional UI pages needs to be implemented | 1. Continue to learn about Spring Security and JWT 2. Will need to coordinate with group and determine which other functionalities are need (utilized PrivatalTracker) 3. Continue to work on UI Pages | 1. Finish frontend/backend integration with Spring Secruity with JWT 2. Determine which other functionalities we should pursuit and divide into sub group accordingly 3. Create Login page, and Staff UI page with functional capabilities | 1. 8hr 2. 1hr 3. 6hr
4 | 9/28-10/3 | 29.5 | 29 | 0.5 | 0 - learn/understand spring security, JWT authentication, React integration 1 - implement request vacation funcationality via TDD method 4 - front/back/security integration testing, request vacation testing 5 - communicate security team for integration | 12 | 3 |  |  | 12 | 2 |  |  | 1. implement request vacation functionality onto backend (currently not rolledout yet) 2. success implement security onto backend for authenication | 1. Intergation of frontend with backend+security is a concern | 1. Continue to learn React/SpringBoot/Security integration | 1. Finish frontend integration with backend+security | 1. 10hr
5 | 10/4-10/10 | 21.5 | 21 | 0.5 | 0 - learn/undersand spring security, JWT, React integration 1 - make login and registration page 4 - integration testing | 10 | 1 |  |  | 10 |  |  |  | 1. sucessful integration of front-back-database-security 2. create LoginPage and RegisterStaff page | 1. role base authorization is a concern | 1. Continue to learn SpringBoot security to implement role base authorization | 1. implement role base authorization 2. implement staff home page and other staff functionalities | 1. 10hr 2. 10hr
6 | 10/10-10/17 | 16 | 12 | 4 | 0 - learn role base authorization 1 - make separate homepage based on role, debug registration page 2 - update SDD UI 5 - schedule final presetation 7 - make final application demo, update privotalTracker | 8 | 2 | 0.5 |  |  | 0.5 |  | 1 | 1. successful made role-base login 2. complete SDD UI documentation 3. finish demo video | 1. still need to implement request vacation 2. still need to implement forget password | 1. implement backend/frontend for request vacation 2. implememt backend/frontend for forget password | 1. implement backend/frontend for request vacation | 6hr

## Yuxuan Wang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05/23-09/12/23 | 10 | 7 | 3 | 0 - learn Git and Spring Boot 1 - team discussion and meeting 5 - make project plan 6 - set up git and working environment | 1 | 3 |  |  |  | 2 | 1 |  | 1. Contribute to SPPP_RiskManagement and SPPP file 2. Set up git, commit a intro paragraph on git | 1. Not familar with Git desktop 2. Not familiar with automated testing tools that can be embedded with Github 3. Not familiar with front-end or db implement with Spring boot | 1.Research Git Desktop tutorial on Youtube 2. Research on thymeleaf package in Spring boot for processing and creating CSS file. Check on integrate database with MySql.(could switch to H2 for its easier and in-memory usage) | 0 - continue learning db and front-end in Spring boot 1 - start build app with team | 10
2 | 9/12/23-9/16/23 | 10 | 8 | 2 | 0. learning Git and Spring boot 1. clarified requirment for project 5. Meet up with group members to assign modules and tasks 6. Set up Junit and Maven environment | 3 | 2 |  |  |  | 2 | 1 |  | 1.Contribute to SPPP file and SDD in Design pattern part 2. Set up Git and separate my own branch and branch for the backend | 1. Not clear with tasks assignment | 1. Set up more meeting with other teammembers to assign tasks 2. Learn Git and Spring boot | 1. Code up for the project | 13
3 | 9/16/23-9/26/23 | 33 | 25 | 8 | 2 - create H2 database schema for project and made plans for databases and backend algorithms. 3- make changes to backend algorithm and add new structures for Junit Tests. 4 - create Junit Tests for backend classes including Model, Controller and Repository for Employee and Credential Parts 5. meet up with Jingjing to configure Git, SpringBoot Maven, H2 dependencies and related work 6. Configure new branch for my own updates and public branch for whole backend & database design 7. Wrote out the design document for backend and database algorithms | 2 |  | 4 | 8 | 1 | 4 | 4 | 2 | 1. Created three database tables using H2 database structure 2.Added multiple Junit Tests Cases for Model, Controller and Repository 3. Coded backend classes for employee and Credentials with all unit tests | 1. Haven't test on the vacation request form part 2. Can't separate classes into different folders with Junit Tests available 3. | 1. Coordinate with other teammembers to code up vacation part or move it into next iteration | 1. Learn integrated testing using Postman or Mokito 2. Code up vacation part | 15
4 | 9/26/23- 10/9/23 | 14 | 10 | 4 | 0- learn about dockerfiles, react test framework 4 - modified unit test coverage for backend,front/back/security integration testing 5 - Did iteration 1 presentation | 5 |  |  |  | 3 | 2 |  |  | 1. Modified unit tests after integration with frontend and security | 1. not familiar to run codes with JWT security 2. not familiar with Docker | 1. Coordinate with other teammembers to test out integration in next interation | 1. Learn integrated testing | 15
5 | 10/9/23- 10/17/23 | 8 | 4 | 4 | 0- learn docker setup for postgres 1 - check up vacation functionality for backend | 2 | 2 | [6 empty] | 6- docker setup for postgres | 1. not familiar to run codes with JWT security 2. not familiar with Docker | 1. Coordinate with other teammembers to check final version of our project |  | 10

## Jingjing Tang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05/23-09/12/23 | 10 | 8 | 2 | 0 - learn Git and Spring Boot 1 - watch team discussion and meeting record 5 - make project plan 6 - set up git and working environment | 3 | 2 |  |  |  | 2 | 1 |  | 1. Contribute to class diagram and SPPP file 2. Set up git, commit a intro paragraph on git | 1. Unfamiliar with Git desktop. 2. Unacquainted with automated testing tools integrated with Github. 3. Unversed in front-end or database implementation using Spring Boot. | 1. Look up Git Desktop tutorials on YouTube. 2. Investigate the Thymeleaf package in Spring Boot for CSS file generation and processing. 3.explore integrating with MySQL. (Consider using H2 for its simplicity and in-memory capabilities.) | 0 - continue learning db and front-end in Spring boot 1 - start build app with team 2 - communicate with group memeber about general design | 10
2 | 09/12/23-09/16/23 | 6 | 4 | 2 | 0 - learning git commands and remote setup 5 - design class diagram 6 - set up git and environment in intellij | 2 |  |  |  |  | 1 | 1 |  |  |  |  | 1. Finish iteration 1 database and backend design 2. Learn the JUnit Test and apply it on the classes | 15
3 | 09/17/23-09/25/23 | 23 | 18.5 | 4.5 | 1 - understand database and backend design requirement for iteration 1 2 - make design plan with Yuxuan 3- make changes to backend algorithm and add new structures for Junit Tests. 4 - create Junit Tests for backend classes including Model, Controller and Repository 5. meet up with Yuxuan to configure Git, SpringBoot Maven, H2 dependencies and related work 6. Configure new branch for my own updates and public branch for whole backend & database design |  | 0.5 | 1 | 10 | 2 | 4 | 1

## Zhiwei Lin
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/05-9/12 | 6 | 5 | 1 | 0 - learn git and springboot, read tutorials about git 1 - watch team discussion and meeting record 2 - make project plan, send reminders to team members | 1 | 2 |  |  |  | 1 | 1 |  | 1.Modified the team.md document and added a self introduction | 1. not familar with github 2. Joined the group later, missed some discussion | 1.Look again at the springboot framework.2.Studying the SpringSecurity | 0 - Studying how to build db 1 - Integrate springboot and Springsecurity | 10
2 | 9/12-9/17 | 6 | 5 | 1 | 0 - learn spring security and database 1 - watch team discussion and meeting record 2 - write part of business logic for our project 6 - I set up an environment on my computer to try to complete the User's CRUD first | 2 | 1 |  |  |  |  | 2 |  | 1. Some basic functions of the system are designed | 1. An error has been reported after some dependencies are imported locally | 1. Studying database 2. Still not sure how to use github | 0. continue to study sprinboot 6. Create several basic data tables to test the user's CRUD | 10
3 | 9/18-9/25 | 14.5 | 13.5 | 1 | 0 - learn spring security and database 1 - watch team discussion and meeting record 2 - Consider the code logic that gets the current role 3 - Create 5 databse table by using MYSQL 4. test after add springsecurite 6 - I set up an environment on my computer and finish writting the User and Role's CRUD. add the methods of assigning roles, search the role of the current user, and return the common result, add swagger2 for testing. add springsecurity part. | 3 | 1.5 | 1 | 2 | 1 |  | 5 |  | 1. The overall project structure is already in place, and basic CRUD for users and roles has been completed, with some new features added 2. finish springsecurity part. | 1. There is a problem about github upload, but I have communicated with TA to deal with it | 1.continue to learn springsecurity | 1. using JWT to verify(finish) 2. The interface that assigns users the permission to add, delete, modify, and query(Finished) | 10
4 | 9-25/9-30 | 12 | 11 | 1 | 0 - learning security 3 - rewrite the project after change to MYSQL | 3 |  | 8 | [5 empty] | 1.rewrite the project after change DB |  |  | hard to integrate | 14
5 | 10/1-10/13 | 2.5 | 1.5 | 1 | 0- learn docker setup | 1.5 | [7 empty] | 1. test for springsecurity | 1. if two same user exist in DB An error will be reported, hard to find it 2. not familar with Docker |  |  | 3

## Weihao Mai
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05-09/12 | 10 | 9 | 1 | 0 - learn Git, Spring Boot and Mysql 1 - watch team discussion and meeting record 5 - make project plan 6 - set up git, java and Mysql environment | 4 | 2 |  |  |  | 1 | 2 |  | 1.Modified the team.md document and added a self introduction | 1. not familar with git and github 2.not know how to push code to github 3. not familar with Mysql 4. not familar with Spring boot | 1. finish Springboot tutorial in 2 weeks, be able to create simple Springboot hello world project next week 2. learn how to build databasr using Mysql | 0 - continue to learnSpringboot and Mysql 1 - continue to define requirements 3 - implement database using Mysql | 9
2 | 9/12-9/17 | 9 | 8 | 1 | 0 - learn spring security and jwt authentication 1 - communicated with team through zoom 2 - write security design for our project 6 - I set up an environment on my computer to try to use Springboot | 2 | 2 |  |  |  | 3 | 1 |  | 1. Some security of the system are designed | 1. An error has been reported after some dependencies are imported locally | 1. Studying jwt authentication 2. Still not sure how to use github | 0. continue to study sprinboot 6. Create several basic data tables to test the user's CRUD | 10
3 | 9/18-9/22 | 9 | 8 | 1 | 0 - learn mock code with Springboot 1 - communicated with team through zoom 2 - design mock test 3 - implement DAO test 6 - I set up an environment on my computer and do some test on DAO and entity | 3 | 1 |  | 2 |  |  | 2 |  | The entire project structure is in place, basic testing of users and roles has been completed, and the project's DAO has been tested | 1. There is a bug about project and I try to deal with it | 1.continue to learn mock test with Springtest | 3. implement other mock test | 10
4 | 9/23-10/8 | 20 | 19 | 1 | 0 - learn/undersand spring security, JWT, React integration and uint test 4 -uint testing | 10 |  |  |  | 9 |  |  |  | 1. finish uint test of spring security 2.java reported an error missing some packages | 1.not familar with uint test | 1.Unit test the backend | 4.Unit test the backend | 10
5 | 10/8-10/17 | 2.5 | 1.5 | 1 | 0- learn docker setup | 1.5 | [7 empty] | 1. test for springsecurity | 1. not familar with Docker |  |  | 3

## Abigya Devkota
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05/23-09/12/23 | 14.5 | 11.5 | 3 | 0 - learn git and spring boot 1 - discuss project with team 5 - make project plan 6 - set up git/springboot/maven 7 - presentation | 3 | 3 |  |  |  | 2 | 3 | 0.5 | 1. Contribute to high level requirements, project time and git guidelines 2. Begin project design for review 3. Participate in Iteration 0 presentation | 1. Deciding on project complexity per team member's familiarity with chosen tech stack 2. Deciding on database that's easy enough to implement with spring boot | 1. Create data model and practice with shell project 2. Research H2 database | 0- continue learning about using db with springboot 2 - build app with team | 10
2 | 9/12/23-9/16/23 | 12 | 9 | 3 | 1- trying to prevent scope creep, be realistic about what we can accomplish given the time we have 2- create architecure design for mvp of project 6- try to convert github shell project to spring boot |  | 1 | 4 |  |  | 4 |  |  | 1. clarify project requirements and scope 2. created diagrams on lucid chart 6- add spring boot project module to exisitng github project | 6- figuring out spring boot package issues when trying to do the conversion | 6- figure out spring boot packaging issue | 6- finalize spring boot use with team, 2. try to build simple web app with React 5. finalize shell project with team | 9
3 | 9/16/23-9/26/23 | 16 | 13 | 3 | 0- learn react.js 5- work with team to combine all components and debug issues 4- test backend , frontend and database to ensure code was runnable and performed minimal functionality 6- combine spring boot project with front end code, created PR for merging | 3 |  |  |  | 8 | 1 | 1 |  | 1 - detailed software architecture for SDD 3 - figured out temporary solution to run the web application using terminal 6- combine frontend backend and database layers 7- worked with team members to fix code issues | 3- temporary fix is not sustainable, we need to use docker to run the application 6- having a maven project within a shell project is confusing and creates weird modules | 0 - learn about docker and using dockerfile 6- cleanup maven configs | 0- dockerize application 3- build ui pages needed for additional features like vacation requests 6- cleanup maven configs | 12
4 | 9/26/23- 10/9/23 | 14 | 10 | 4 | 0- learn about dockerfiles, react test framework 4 - added unit test coverage for ui pages 6 - added docker setup to run front end and backend seamlessly | 2 |  |  |  | 4 |  | 4 |  | 4 - test coverage for ui 6 - dockerizing the application | 4 - there are many ui test frameworks and it is difficult to find the right one 6- need to redo docker setup using postgres | 4 - try to add more ui tests with mocking api calls | 6 - look into application deployment | 10
5 | 10/9/23- 10/17/23 | 14 | 10 | 4 | 0- learn docker setup for postgres 6- add docker setup for postres | 2 |  |  |  | 4 |  | 4 |  | 6- docker setup for postgres | 0- big learning curve for postgres docker setup and port forwarding, 0 - couldn't look into application deployment due to time constraint 6- redid docker setup for postgres but was difficult for other team members to adapt on their machine | 0- continue to learn dockerfile and docker compose setup |  | 10