## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 2 | 2 | 32 | team leader and all members | 2023-10-20 | Redefine the project scope if necessary, and assign the tasks to other team members. | One new person has been added | Open
| add new team members | one or more team member gets added | 2 | 2 | 2 | 32 | team leader and all members | 2023-10-20 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one added to class so far | Open
| Lack of motivation or responsibility | One or more team member lacks motivation/responsbility | 2 | 2 | 2 | 32 | team leader and all members | 2023-10-20 | Redefine the project scope if necessary, and assign the tasks to other team members. | Everyone is on track | Open
Communication | duplicate work | Two or more team member does the same work | 2 | 3 | 2 | 24 | team leader and all members | 2023-10-20 | Define work more details | no current duplicated work | Open
| worked on wrong components | One or more team member worked on the wrong part of assignement | 2 | 3 | 2 | 24 | team leader and all members | 2023-10-20 | revist project every iteration | no current wrong components being worked on | Open
| useless work | One or more team member does ineffective work | 2 | 3 | 2 | 24 | team leader and all members | 2023-10-20 | plan ahead and stick to it | no current useless work | Open
| inconsistent work | change idea or structure 2 weeks after begining | 2 | 3 | 2 | 24 | team leader and all members | 2023-10-20 | plan ahead and stick to it | no inconsistent work | Open
Requirements | unclear requirements | vague or ambiguous descriptions of function requirements, so unabale to implement | 2 | 4 | 3 | 24 | design and implementation manager and all members | 2023-10-20 | need to be detailed when creating the design documents. | all current work are well defined | open
| scope creep | add too many deliveables in the middle of the project | 1 | 4 | 2 | 20 | team leader and all members | 2023-10-20 | plan ahead and stick to it | No one added to class so far | Open
| constant requirements changes | some functions is no longer needed, or change to other functions | 2 | 3 | 2 | 24 | design and implementation manager and all members | 2023-10-20 | All team member will participate in meeting and will weight risk of finishing project vs. chaning requirement | no change of requirement at this moment | Open
Management | improper task assignments | task assigned improperly | 2 | 2 | 2 | 32 | team leader and all members | 2023-10-20 | All team member will voice their improper task assignment | no improper task are being assigned at this moment | Open
| improper planning | task planned improperly | 2 | 2 | 2 | 32 | team leader and all members | 2023-10-20 | All team member will voice their concern on improper planning | no improper planning at this moment | Open
| lack of management skills | One or more Team member lack of management skills | 2 | 2 | 2 | 32 | team leader and all members | 2023-10-20 | All team member will voice their concern on lack of management | no concerns of management at this moment | Open
Technology competence | Not familiar with the framework used | One or more Team member unfamiliar with SpringBoot | 4 | 4 | 3 | 12 | team leader and all members | 2023-10-20 | All team member will engage in self learning of SpringBoot and will actively seek help from other member if necessary | Self-paced learning of SpringBoot | open
| Not familiar with the programming language used | One or more Team member unfamiliar with programming language | 4 | 4 | 3 | 12 | team leader and all members | 2023-10-20 | All team member will engage in self learning of Java and will actively seek help from other member if necessary | Self-paced learning of Java | open
| Not familiar with unit testing | One or more Team member unfamiliar with unit testing | 4 | 4 | 3 | 12 | team leader and all members | 2023-10-20 | All team member will engage in self learning of Junit and will actively seek help from other member if necessary | Self-paced learning of Junit | open
| Other technology incompetence | known technology tech stack does not compete with Spring boot | 4 | 4 | 3 | 12 | team leader and all members | 2023-10-20 | All team member will engage in self learning of any other technology stack and will actively seek help from other member if necessary | Self-paced learning of new stack | open
| Not familiar with Git | One or more Team member unfamiliar with Git | 4 | 4 | 3 | 12 | team leader and all members | 2023-10-20 | All team member will engage in self learning of Git and will actively seek help from other member if necessary | Self-paced learning of Git | open
Design and implementation | Improper design | poor design which does not fill coding standards | 4 | 3 | 3 | 18 | team leader and all members | 2023-10-20 | All members should continuously review the application design | Self review of design implementation as well as biweekly team meeting to further discuss any change/improvement to the current design | open
| improper technology stack | SpringBoot does not satisify all our requirements | 1 | 4 | 2 | 20 | team leader and all members | 2023-10-20 | All team member will discuss and evalute the risk of implementing new tech stack vs. continuing current tech stack | Current tech stack satisfies our requirements | Open
| Messy code | Code not following code standards | 2 | 3 | 2 | 24 | team leader and all members | 2023-10-20 | Codes will be reviewed by everyone before merging into the Masters | Codes will be reviewed prior to merge | open
Testing | Not enough testing | testing units are below sufficient | 3 | 2 | 2 | 24 | team leader and all members | 2023-10-20 | more unit tests are asked to create for the defect parts and fail edge cases | enough unit tests are generated | open
Integration and deployment | Not enough time for integration and deployment | no time for integration and deployment | 3 | 1 | 1 | 15 | team leader and all members | 2023-10-20 | We will focus on the core functionality of the application and all team member will review additional funcitonalities and budget time accordingly. | Primarly focus on core functionalities and additional features will be reviewed against time constrains | open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.