## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrenc e (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer team leader and all members | Target completion date | Detailed plan | Execution summary | Status Open | Last reivewed
personel | Loss team members | One or more team members drop the class | 1 | 1 | 2 | 50 | team leader and all members | 2023-10-17 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one left class so far | closed | 2023-10-17
| add new team members | one or more team member gets added | 1 | 1 | 2 | 50 | team leader and all members | 2023-10-17 | Redefine the project scope if necessary, and assign the tasks to other team members. | 1 person was added to the group | closed | 2023-10-17
| Lack of motivation or responsibility | One or more team member lacks motivation/responsbility | 2 | 2 | 2 | 32 | team leader and all members | 2023-10-17 | Redefine the project scope if necessary, and assign the tasks to other team members. | Decrease risk as project is near end | closed | 2023-10-17
Communication | duplicate work | Two or more team member does the same work | 1 | 3 | 2 | 30 | team leader and all members | 2023-09-25 | Backend: Yuxuan, Jingjing, Haolun Frontend: Jianle, Abigya Security:Zhiwei, Weihao Backend-Front integeration and then apply security | Workload has been divided into 3 component: front, back, security Duplicated work risk should decrease more as near end of project | closed | 2023-10-17
| worked on wrong components | One or more team member worked on the wrong part of assignement | 1 | 2 | 1 | 20 | team leader and all members | 2023-10-20 | Team Lead will have to review each sub-team's work on regular basis to ensure that all members on track for their tasks plan ahead and stick to it | will continue to engage with all team member | open | 2023-10-17
| useless work | One or more team member does ineffective work | 2 | 3 | 2 | 24 | team leader and all members | 2023-10-20 | Team Lead will have to review each sub-team's work on regular basis to ensure that all members on track for their tasks | No current useless | open | 2023-10-17
| inconsistent work | Change idea or structure 2 weeks after begining | 1 | 2 | 1 | 20 | team leader and all members | 2023-10-20 | Team lead will continously engage with team member. | work will continue to engage with all team member | open | 2023-10-17
| inconsistent communication | One or more team member does not engage in group | 1 | 2 | 1 | 20 | team leader and all members | 2023-10-20 | Team member have to response back to Team lead within reasonable time | will continue to engage with all team member decrease risk as few as near project deadline | open | 2023-10-17
Requirements | unclear requirements | vague or ambiguous descriptions of function requirements, so unabale to implement | 1 | 4 | 3 | 30 | design and implementation manager and all members | 2023-09-05 | Requirement are more detailed in the SPPP and SDD | Current work are more defined | closed | 2023-10-17
| scope creep | add too many deliveables in the middle of the project | 1 | 4 | 2 | 20 | team leader and all members | 2023-09-05 | Focusing on our primary functionalities first before implementing other desirables | core function CRUD achieved | open | 2023-10-17
| constant requirements changes | some functions is no longer needed, or change to other functions | 1 | 3 | 2 | 30 | design and implementation manager and all members | 2023-10-20 | Focusing on our primary functionalities first before implementing other desirables | core function CRUD | closed | 2023-10-17
Management | improper task assignments | task assigned improperly | 2 | 2 | 2 | 32 | team leader and all members | 2023-10-20 | All team member will voice their improper task assignment | no improper task are being assigned at this moment | Open | 2023-10-17
| improper planning | task planned improperly | 3 | 4 | 3 | 18 | team leader and all members | 2023-10-20 | Reiterate that all team member will voice their concern on improper planning Need a better way to identify bottleneck processes and/or ways to allocate work resource more efficiently | Team member should voice their concern on lack of and/or too much workload | Open | 2023-10-17
Technology competence | Not familiar with the framework used | One or more Team member unfamiliar with SpringBoot | 1 | 4 | 3 | 30 | team leader and all members | 2023-10-20 | All team member will engage in self learning of SpringBoot and will actively seek help from other member if necessary | Self-paced learning of SpringBoot decreased risk as time goes on | closed | 2023-10-17
| Not familiar with the programming language used | One or more Team member unfamiliar with programming language | 1 | 4 | 3 | 30 | team leader and all members | 2023-10-20 | All team member will engage in self learning of Java and will actively seek help from other member if necessary | Self-paced learning of Java decrease risk as time goes on | closed | 2023-10-17
| Not familiar with unit testing | One or more Team member unfamiliar with unit testing | 1 | 3 | 3 | 45 | team leader and all members | 2023-10-20 | All team member will engage in self learning of Junit and will actively seek help from other member if necessary | Self-paced learning of Junit decrease risks as every member is required to submit their own tests | closed | 2023-10-17
| Other technology incompetence | known technology tech stack does not compete with Spring boot | 2 | 4 | 3 | 24 | team leader and all members | 2023-10-20 | All team member will engage in self learning of any other technology stack and will actively seek help from other member if necessary | Self-paced learning of new stack | open | 2023-10-17
| Not familiar with Git | One or more Team member unfamiliar with Git | 2 | 4 | 3 | 24 | team leader and all members | 2023-10-20 | All team member will engage in self learning of Git and will actively seek help from other member if necessary | Self-paced learning of Git | open | 2023-10-17
| Not familiar integrating different tech stack | One or no member is familiary with integrating different parts of tech stack | 3 | 4 | 3 | 18 | team leader and all members | 2023-10-20 | All team member will need to video record their expertise on their part of the project as well as learn from other member's tech expertise | self learning, engage with other memebers, and watch their tech expertise demos | open | 2023-10-17
Design and implementation | Improper design | poor design which does not fill coding standards | 1 | 3 | 4 | 60 | team leader and all members | 2023-10-20 | All members should continuously review the application design | Self review of design implementation as well as biweekly team meeting to further discuss any change/improvement to the current design risks are decrease | closed | 2023-10-17
| improper technology stack | SpringBoot does not satisify all our requirements | 1 | 4 | 4 | 40 | team leader and all members | 2023-10-09 | All team member will discuss and evalute the risk of implementing new tech stack vs. continuing current tech stack | Current tech stack satisfies our requirements | closed | 2023-10-17
| Messy code | Code not following code standards | 1 | 2 | 2 | 40 | team leader and all members | 2023-10-20 | Codes will be reviewed by everyone before merging into the Masters | Codes will be reviewed prior to merge | closed | 2023-10-17
Testing | Not enough testing | testing units are below sufficient | 1 | 2 | 2 | 40 | team leader and all members | 2023-10-20 | more unit tests are asked to create for the defect parts and fail edge cases | enough unit tests are generated risks are decreased | closed | 2023-10-17
Integration and deployment | Not enough time for integration and deployment | no time for integration and deployment | 3 | 1 | 2 | 30 | team leader and all members | 2023-10-20 | We will focus on the core functionality of the application and all team member will review additional funcitonalities and budget time accordingly. | Primarly focus on core functionalities and additional features will be reviewed against time constrains | closed | 2023-10-17